## Schedule
Iteration No | Task ID | Description | Type | PLANNED DATETIME START | PLANNED DATETIME END | HOURS SPENT PLANNED | ACTUAL DATETIME START | ACTUAL DATETIME END | HOURS SPENT ACTUAL | STATUS | Est Days | Act Days | Planned Prog Hrs | Prog Hrs | Non-Prog Hrs | ItrStatus | ItrNot planned
1 | 1 | Weekly Meeting (1) | Team Meeting - Planning, Admin, & Updates | 2021-01-14 | 2021-01-14 | 3 | 2021-01-14 | 2021-01-14 | 3 | Completed | 0 | 0 | 0 | 0 | 3 | 1Completed | 1
1 | 2 | Develop Project Schedule - Identify the tasks needed - prepare the necessary files - create git hub | Project Management - Update Schedule | 2021-01-14 | 2021-01-14 | 0.5 | 2021-01-14 | 2021-01-14 | 0.5 | Completed
1 | 3 | Distribution of Roles and Responsibilities | Team Meeting - Planning, Admin, & Updates | 2021-01-14 | 2021-01-14 | 0.5 | 2021-01-14 | 2021-01-14 | 0.5 | Completed
1 | 4 | Define use cases | Pricing Model - Research | 2021-01-14 | 2021-01-14 | 0.5 | 2021-01-14 | 2020-01-14 | 0.5 | Completed
1 | 5 | Weekly Meeting (2) | Team Meeting - Planning, Admin, & Updates | 2021-01-21 | 2021-01-21 | 3 | 2020-01-21 | 2020-01-21 | 3 | Completed
| 6 | Data Collection | Data Preparation (Both) | 2021-01-22 | 2021-01-23 |  | 2021-01-22 | 2021-01-23 |  | Completed
1 | 6_1 | Data Collection (Pricing Models) | Pricing Model - Data Preparation | 2021-01-22 | 2021-01-23 | 2 | 2021-01-22 | 2021-01-23 | 2 | Completed
1 | 6_2 | Data Collection (PED) | PED - Data Preparation | 2021-01-22 | 2021-01-23 | 1 | 2021-01-22 | 2021-01-23 | 2 | Completed
1 | 7 | Research Analysis | Deliverable Preparation | 2021-01-23 | 2021-01-27 |  | 2021-01-23 | 2021-01-27 |  | Completed
1 | 7_1 | Literature research for PED - Market Research on products’ elasticity - Selection of relevant Ecommerce products | PED - Research | 2021-01-23 | 2021-01-27 | 5 | 2021-01-23 | 2021-01-27 | 5 | Completed
1 | 7_2 | Literature research for Pricing Model - Pricing Problems in Industry & Machine Learning Models - Attributes affecting price of products | Pricing Model - Research | 2021-01-23 | 2021-01-27 | 5 | 2021-01-23 | 2021-01-27 | 5 | Completed
1 | 8 | Case study Analysis | PED - Analysis | 2021-01-26 | 2021-01-27 | 2 | 2021-01-26 | 2021-01-27 | 2 | Completed
2 | 9 | Weekly Meeting (3) | Team Meeting - Planning, Admin, & Updates | 2021-01-28 | 2021-01-28 | 3 | 2020-01-28 | 2020-02-04 | 3 | Completed
2 | 10 | Exploratory Data Analysis & Visualisation | Data Preparation (Both) | 2021-01-29 | 2021-01-31 |  | 2020-01-29 | 2020-01-31 |  | Completed
2 | 10_1 | Exploratory Data Analysis & Visualisation (Pricing model) | Pricing Model - Data Preparation | 2021-01-29 | 2021-01-31 | 5 | 2020-01-29 | 2020-01-31 | 5 | Completed
2 | 10_2 | Exploratory Data Analysis & Visualisation (PED) | PED - Data Preparation | 2021-01-29 | 2021-01-31 | 5 | 2020-01-29 | 2020-01-31 | 5 | Completed
2 | 11 | Data Pre-processing & Cleaning (Both PED & Pricing Model) - part 1 | Data Preparation (Both) | 2021-02-01 | 2021-02-01 |  | 2020-02-01 | 2020-02-01 |  | Completed
2 | 11_1 | Handle missing value | Data Preparation (Both) | 2021-02-01 | 2021-02-01 | 1 | 2020-02-01 | 2020-02-01 | 1 | Completed
2 | 11_2 | Change data type | Data Preparation (Both) | 2021-02-01 | 2021-02-01 | 1 | 2020-02-01 | 2020-02-01 | 1 | Completed
2 | 12 | Weekly Meeting (4) | Team Meeting - Planning, Admin, & Updates | 2021-02-04 | 2021-02-04 | 3 | 2021-02-04 | 2021-02-04 | 3 | Completed
2 | 13 | Data Pre-processing & Cleaning (Both PED & Pricing Model) - part 2 | Data Preparation (Both) | 2021-02-05 | 2021-02-09 |  | 2020-02-05 | 2020-02-09 |  | Completed
2 | 13_1 | Data Transformation | Data Preparation (Both) | 2021-02-05 | 2021-02-09 | 2 | 2020-02-05 | 2020-02-09 | 4 | Completed
2 | 13_2 | Outlier Management | Data Preparation (Both) | 2021-02-05 | 2021-02-09 | 2 | 2020-02-05 | 2020-02-09 | 4 | Completed
2 | 13_3 | Categorical Encoding | Data Preparation (Both) | 2021-02-05 | 2021-02-09 | 2 | 2020-02-05 | 2020-02-09 | 4 | Completed
2 | 14 | Buffer |  | 2021-02-10 | 2021-02-11 |  | 2020-02-10 | 2020-02-11 |  | Completed
3 | 15 | Weekly Meeting (5) | Team Meeting - Planning, Admin, & Updates | 2021-02-11 | 2021-02-11 | 3 | 2020-02-11 | 2020-02-18 | 3 | Completed
3 | 16 | Preliminary Analysis (Pricing Model) - part 1 |  | 2021-02-12 | 2021-02-17 |  | 2020-02-12 | 2020-02-17 |  | Completed
3 | 16_1 | Feature Selection | Pricing Model - Data Preparation | 2021-02-12 | 2021-02-13 | 2 | 2020-02-12 | 2020-02-13 | 2 | Completed
3 | 16_2 | Feature Engineering - NLP on attributes | Pricing Model - Data Preparation | 2021-02-12 | 2021-02-13 | 2 | 2020-02-12 | 2020-02-13 | 2 | Completed
3 | 17 | Baseline Modelling (Pricing model) | Pricing Model - Modelling | 2021-02-14 | 2021-02-17 |  | 2021-02-14 | 2021-02-17 |  | Completed
3 | 17_1 | Baseline Modelling - LightGBM | Pricing Model - Modelling | 2021-02-14 | 2021-02-17 | 5 | 2020-02-14 | 2020-02-17 | 10 | Completed
3 | 17_2 | Baseline Modelling - Linear Regression | Pricing Model - Modelling | 2021-02-14 | 2021-02-17 | 5 | 2020-02-14 | 2020-02-17 | 10 | Completed
3 | 17_3 | Baseline Modelling - KNN | Pricing Model - Modelling | 2021-02-14 | 2021-02-17 | 5 | 2020-02-14 | 2020-02-17 | 10 | Completed
3 | 18 | Preliminary Analysis (PED) - part 1 | PED - Analysis | 2021-02-12 | 2021-02-17 |  | 2020-02-12 | 2020-02-17 |  | Completed
3 | 18_1 | Data Preprocessing | PED - Analysis | 2021-02-12 | 2021-02-14 | 4 | 2020-02-12 | 2020-02-14 | 5 | Completed
3 | 18_2 | Visualisation | PED - Analysis | 2021-02-14 | 2021-02-17 | 3 | 2020-02-14 | 2020-02-17 | 5 | Completed
3 | 18_3 | Regression Modelling & Visualizations | PED - Modelling | 2021-02-14 | 2021-02-17 | 5 | 2020-02-14 | 2020-02-17 | 10 | Completed
3 | 19 | Weekly Meeting (6) | Team Meeting - Planning, Admin, & Updates | 2021-02-18 | 2021-02-18 | 1.5 | 2021-02-18 | 2021-02-18 | 1.5 | Completed
3 | 20 | Baseline Modelling (Pricing model) | Pricing Model - Modelling | 2021-02-19 | 2021-02-22 |  | 2021-02-19 | 2021-02-22 |  | Completed
3 | 20_1 | Baseline Modelling - Random Forest | Pricing Model - Modelling | 2021-02-19 | 2021-02-22 | 5 | 2021-02-19 | 2021-02-22 | 10 | Completed
3 | 20_2 | Baseline Modelling - Neural Networks | Pricing Model - Modelling | 2021-02-19 | 2021-02-22 | 5 | 2021-02-19 | 2021-02-22 | 10 | Completed
3 | 21 | Regression Analysis & PED Calculations | PED - Analysis | 2021-02-19 | 2021-02-22 | 5 | 2021-02-19 | 2021-02-22 | 10 | Completed
3 | 22 | Prepare slides for Mid-Term Presentation | Milestone - Preparation | 2021-02-23 | 2021-02-23 | 3 | 2021-02-23 | 2021-02-23 | 3 | Completed
3 | 23 | Buffer |  | 2021-02-24 | 2021-02-24 |  | 2021-02-24 | 2021-02-24 |  | Completed
4 | 24 | Weekly Meeting (7) | Team Meeting - Planning, Admin, & Updates | 2021-02-25 | 2021-02-25 | 1.5 | 2021-02-25 | 2021-02-25 | 1.5 | Completed
4 | 25 | Preliminary Analysis (Pricing Model) - part 3 |  |  |  | 0 |  |  |  | Completed
4 | 25_1 | Baseline Modelling - Lasso | Pricing Model - Modelling | 2021-02-25 | 2021-03-02 | 5 | 2021-02-19 | 2021-02-22 | 10 | Completed
4 | 25_2 | Baseline Modelling - XGBoost | Pricing Model - Modelling | 2021-02-25 | 2021-03-02 | 5 | 2021-02-19 | 2021-02-22 | 10 | Completed
4 | 26 | Drawing conclusions and analyses based on visualisations | PED - Analysis | 2021-02-25 | 2021-03-01 | 3 | 2021-02-25 | 2021-03-01 | 3 | Completed
4 | 27 | Buffer |  | 2021-03-03 | 2021-03-03 |  | 2021-03-03 | 2021-03-03 |  | Completed
4 | 28 | Weekly Meeting (8) | Team Meeting - Planning, Admin, & Updates | 2021-03-04 | 2021-03-04 | 1.5 | 2021-03-04 | 2021-03-04 | 1.5 | Completed
4 | 29 | Select best performing Baseline Model | Pricing Model - Modelling | 2021-03-05 | 2021-03-05 | 1 | 2021-03-05 | 2021-03-05 | 1 | Completed
4 | 30 | Documentation of work | Project Management - Other | 2021-03-06 | 2021-03-06 | 2 | 2021-03-06 | 2021-03-06 | 2 | Completed
4 | 31 | Mid Term Presentation Preparation - Group rehearsal for Mid-term presentation | Milestone - Presentations | 2021-03-08 | 2021-03-10 | 3 | 2021-03-08 | 2021-03-10 | 3 | Completed
4 | 32 | Milestone 1: Mid Term Presentation | Milestone - Presentations | 2021-03-10 | 2021-03-10 | 1.5 | 2021-03-10 | 2021-03-10 |  | Completed
5 | 33 | Weekly Meeting (9) | Team Meeting - Planning, Admin, & Updates | 2021-03-11 | 2021-03-11 | 1.5 | 2021-03-11 | 2021-03-11 | 1.5 | Completed
5 | 34 | Mid term feedback review | Milestone - Presentations | 2021-03-12 | 2021-03-12 | 1 | 2021-03-12 | 2021-03-12 | 2 | Completed
5 | 35 | Distribution & refinement of new duties based on feedback | Team Meeting - Planning, Admin, & Updates | 2021-03-12 | 2021-03-12 | 1 | 2021-03-12 | 2021-03-12 | 1 | Completed
5 | 36 | Hyperparameter Tuning | Pricing Model - Modelling | 2021-03-13 | 2021-03-16 | 10 | 2021-03-13 | 2021-03-16 | 6 | Completed
5 | 37 | UI Creation PED | UI Creation | 2021-03-13 | 2021-03-16 | 5 | 2021-03-13 | 2021-03-16 | 4 | Completed
5 | 38 | Buffer |  | 2021-03-17 | 2021-03-17 |  | 2021-03-17 | 2021-03-17 |  | Completed
5 | 39 | Weekly Meeting (10) | Team Meeting - Planning, Admin, & Updates | 2021-03-18 | 2021-03-18 | 1.5 | 2021-03-18 | 2021-03-18 | 1.5 | Completed
5 | 40 | Model boosting | Pricing Model - Modelling | 2021-03-19 | 2021-03-20 | 5 | 2021-03-19 | 2021-03-20 | 6 | Completed
5 | 41 | Final Model Prediction | Pricing Model - Modelling | 2021-03-21 | 2021-03-23 | 5 | 2021-03-21 | 2021-03-23 | 6.5 | Completed
5 | 42 | UI Creation (Pricing Model) | UI Creation | 2021-03-19 | 2021-03-23 | 5 | 2021-03-19 | 2021-03-23 | 3 | Completed
5 | 43 | Buffer |  | 2021-03-24 | 2021-03-24 |  | 2021-03-24 | 2021-03-24 |  | Completed
6 | 44 | Weekly Meeting (11) | Team Meeting - Planning, Admin, & Updates | 2021-03-25 | 2021-03-25 | 1.5 | 2021-03-25 | 2021-03-25 | 1 | Completed
6 | 45 | Report write up | Deliverable Preparation | 2021-03-26 | 2021-03-28 | 5 | 2021-03-26 | 2021-03-28 | 4 | Completed
6 | 46 | Model Explanation - part 1 |  | 2021-03-26 | 2021-03-31 |  | 2021-03-26 | 2021-03-31 |  | Completed
6 | 46_1 | Local Interpretable Model-agnostic Explanations (LIME) | Pricing Model - Analysis | 2021-03-26 | 2021-03-31 | 5 | 2021-03-26 | 2021-03-31 | 2 | Completed
6 | 46_2 | Shapley Additive Explanation (SHAP) | Pricing Model - Analysis | 2021-03-26 | 2021-03-31 | 5 | 2021-03-26 | 2021-03-31 | 2 | Completed
6 | 47 | Weekly Meeting (12) | Team Meeting - Planning, Admin, & Updates | 2021-04-01 | 2021-04-01 | 1.5 | 2021-04-01 | 2021-04-01 | 1 | Completed
6 | 48 | Report write up | Deliverable Preparation | 2021-04-02 | 2021-04-03 | 3 | 2021-04-02 | 2021-04-03 | 3 | Completed
6 | 49 | Model Explanation - part 2 |  | 2021-04-03 | 2021-04-07 |  | 2021-04-03 | 2021-04-07 |  | Completed
6 | 49_1 | Local Interpretable Model-agnostic Explanations (LIME) | Pricing Model - Analysis | 2021-04-02 | 2021-04-07 | 5 | 2021-04-02 | 2021-04-07 | 3 | Completed
6 | 49_2 | Shapley Additive Explanation (SHAP) | Pricing Model - Analysis | 2021-04-02 | 2021-04-07 | 5 | 2021-04-02 | 2021-04-07 | 3 | Completed
7 | 50 | Weekly Meeting (13) | Team Meeting - Planning, Admin, & Updates | 2021-04-08 | 2021-04-08 | 1.5 | 2021-04-08 | 2021-04-08 | 1 | Completed
7 | 51 | Final Term Presentation Preparation | [7 empty] | Completed
7 | 51_1 | Report finalisation | Deliverable Preparation | 2021-04-08 | 2021-04-12 | 1 | 2021-04-08 | 2021-04-12 | 1 | Completed
7 | 51_2 | Poster creation | Deliverable Preparation | 2021-04-08 | 2021-04-12 | 3 | 2021-04-08 | 2021-04-12 | 2 | Completed
7 | 51_3 | Preparation of slides for final presentation | Deliverable Preparation | 2021-04-12 | 2021-04-13 | 3 | 2021-04-12 | 2021-04-13 | 2 | Completed
7 | 51_4 | Group rehearsal for final presentation | Deliverable Preparation | 2021-04-13 | 2021-04-13 | 1 | 2021-04-13 | 2021-04-13 | 1.5 | Completed
7 | 52 | Milestone 2: Final Presentation | Milestone - Presentations | 2021-04-26 | 2021-04-26 | 1 | 2021-04-26 | 2021-04-26 | 1 | Completed

## Metrics
Burndown
Iteration No. | Planned | Actual
1 | 200 | 200
2 | 176 | 170
3 | 122.5 | 78.5
4 | 99 | 46.5
5 | 64 | 15
6 | 33 | -4
7 | 22.5 | -12.5

## Config
Leader
Attendee
Data Preparation (Both)
Deliverable Preparation
Deployment
Milestone - Preparation
Milestone - Presentations
Model Selection / Testing
PED - Analysis
PED - Data Preparation
PED - Modelling
PED - Research
Pricing Model - Analysis
Pricing Model - Data Preparation
Pricing Model - Modelling
Pricing Model - Research
Programming - Debugging
Project Management - Other
Project Management - Update Metrics
Project Management - Update Schedule
Team Meeting - Planning, Admin, & Updates
UI Creation
Yes
No
Not started
Started
Completed
Incomplete
Hold